## Read me
SIMULATED: fictional company, synthetic data, no real audit.
Workbook: ai-governance-workbook. Generated by the scripts listed in docs/artifact-index.md from the shared synthetic datasets.
On every sheet the header is row 2, headers are frozen, and filters are on. Empty cells mean no value.
Columns such as status, severity or decision have a drop-down list of the values currently in use; extend the list if you add a new value.
Dates are ISO 8601 (YYYY-MM-DD). Nothing here is client data or an assurance opinion.
Sheets:
Inventory: 2 rows, 26 columns
Assessments: 22 rows, 13 columns
Risk register: 22 rows, 12 columns
Gates: 16 rows, 9 columns
Control mapping: 50 rows, 10 columns
Monitoring: 10 rows, 8 columns
Supplier checklist: 14 rows, 7 columns

## Inventory
SIMULATED: fictional company, synthetic data, no real audit.
use_case_id | name | purpose | business_owner_role | users | data_categories | data_classification | affected_parties | model_provider_type | vendor_id | human_oversight_proposed | intake_date | status | vendor_name | vendor_residual_risk_project3 | inherent_risk | residual_as_proposed | target_residual_after_gates | decision | decision_date | scope_of_decision | gates_total | gates_done | residual_acceptance_authority_after_gates | residual_acceptance_authority_as_proposed | review_cadence
AI-01 | Customer Support Response Assistant | Draft replies to customer support tickets using approved knowledge-base content for agent review | Head of Customer Support | Customer support agents (about 60) | Customer name, account identifiers, ticket text; approved knowledge articles | Confidential | Business customers and their users who receive responses | Third-party hosted LLM API with retrieval over the approved knowledge base | V-03 | Agent reviews and sends every response (proposed); no automatic sending | 2026-07-06 | Pilot gated | Lumenvale AI Ltd. | High | High | High | Medium | Conditionally approved (limited pilot) | 2026-09-24 | Pilot with at most 10 agents, retrieval over approved knowledge-base articles only, API tier only, no automatic sending. Go-live only when gates AI-01-G01 to G08 are evidenced. | 8 | 0 | AI Governance Committee | Chief Risk Officer (executive acceptance) | Monthly for 6 months, then quarterly
AI-02 | Policy and Procedure Document Analyser | Summarise internal policy and procedure documents and answer questions about them for employees | Chief Financial Officer | Employees in Risk, Compliance, Finance and Legal (about 70) | Internal policies, procedures, contracts and board papers that may include confidential and personal information | Confidential | Employees; indirectly customers and counterparties named in documents | Same third-party LLM provider, document-upload tier | V-03 | Users are expected to verify summaries against source documents (no technical control proposed) | 2026-07-20 | Not approved | Lumenvale AI Ltd. | High | High | High | Medium | Not approved: must not proceed | 2026-09-24 | No use of the document-upload tier or any external AI service with Northstar internal documents until gates AI-02-G01 to G08 are evidenced and the use case is resubmitted. Interim: employees must not upload Northstar documents to Lumenvale. | 8 | 0 | AI Governance Committee | Chief Risk Officer (executive acceptance) | Resubmission after gates; then quarterly

## Assessments
SIMULATED: fictional company, synthetic data, no real audit.
assessment_id | use_case_id | risk_area | inherent_rating | residual_as_proposed | residual_after_gates | scoring_rationale | controls_required | gate_ids | monitoring_measure | northstar_control | unified_control | ai_rmf_refs
AIA-01-01 | AI-01 | Intended purpose and affected people | Medium | Medium | Low | Customers receive replies drafted by AI. Business customers could act on wrong information, but every reply is meant to be sent by an agent. | Approved-content retrieval only; agent sends every reply. |  | Complaints attributable to AI-drafted replies | NS-AIG-01 | UC-AIG-01 | MAP 1.1;MAP 3.2;MAP 5.1
AIA-01-02 | AI-01 | Business criticality and fallback | Medium | Medium | Low | Support is customer-facing but a manual process exists, so the service can run without the tool. | Documented manual fallback; ability to disable the tool within one hour. |  | Tool availability and fallback drills | NS-AIG-01 | UC-AIG-01 | MAP 1.4;MANAGE 2.4
AIA-01-03 | AI-01 | Data categories, privacy and confidentiality | High | High | Medium | Ticket text and account identifiers (Confidential personal and account information) go to a third-party model hosted in the United States (assumed) under unclear retention terms. | Redact identifiers before sending where possible; contract states retention and no training use for the API tier; privacy impact assessment (NS-PRV-01) including cross-border handling. | AI-01-G03 | Privacy incidents and redaction failure rate | NS-AIG-01 | UC-AIG-01 | MEASURE 2.10;GOVERN 1.1
AIA-01-04 | AI-01 | Output reliability and hallucination | High | High | Medium | Generated text can be fluent and wrong. A wrong answer about fees, deadlines or service status could harm a customer. | Answers limited to retrieved approved articles with the source article cited; pre-deployment evaluation on a representative ticket set; sampled quality review in operation. | AI-01-G05 | Material error rate from sampled review | NS-AIG-03 | UC-AIG-03 | MEASURE 2.5;MEASURE 2.3;MAP 2.2
AIA-01-05 | AI-01 | Human oversight | High | Medium | Low | The intake proposes agent review of every reply, but no technical control stops a send without review, and agents may approve routinely (automation bias). | Send blocked until the agent approves in the tool; agent training; edit rate and rubber-stamp rate tracked (NS-AIG-02). | AI-01-G04 | Human edit rate and approval time | NS-AIG-02 | UC-AIG-02 | MAP 3.5;GOVERN 3.2
AIA-01-06 | AI-01 | Security: prompt injection and data leakage | High | High | Medium | Customer ticket text is untrusted input and can contain instructions aimed at the model (prompt injection). Retrieved content or other customers' data could be exposed. | Retrieval limited to approved articles; no tool or system actions available to the model; output filtering; red-team tests with injection strings before launch. | AI-01-G06 | Injection test results and blocked-output counts | NS-AIG-01 | UC-AIG-01 | MEASURE 2.7
AIA-01-07 | AI-01 | Supplier and subprocessor dependency | High | High | Medium | Lumenvale AI Ltd. (V-03) has unclear retention, model training, subprocessor and incident terms and High residual risk in Project 3. | Close the Project 3 conditions for the API tier before go-live; exit plan to revert to manual drafting. | AI-01-G01 | Open Project 3 issues for V-03 | NS-SUP-01 | UC-SUP-01 | GOVERN 6.1;MAP 4.1;MANAGE 3.1
AIA-01-08 | AI-01 | Logging and traceability | Medium | Medium | Low | Without logs, an incorrect reply cannot be traced to its prompt, source articles and approving agent. | Log prompt, retrieved article ids, draft, final reply and approver, retained for a stated period (proposed 90 days). | AI-01-G07 | Log completeness check | NS-AIG-03 | UC-AIG-03 | MEASURE 2.8;MANAGE 4.1
AIA-01-09 | AI-01 | Change management (model and vendor changes) | Medium | Medium | Low | A silent model or vendor change can alter behaviour or data handling. | Pin the model version where offered; vendor must give notice of model and terms changes; re-run the evaluation set after any change. |  | Change notices received and re-tests completed | NS-AIG-03 | UC-AIG-03 | MANAGE 4.2;MEASURE 2.4
AIA-01-10 | AI-01 | Accessibility and fairness | Medium | Medium | Low | Tone and clarity may differ for customers who write in non-standard English or in French, and replies must be accessible. | Evaluate on a mix of writing styles and languages; agents can rewrite freely. |  | Complaints by language and quality sample by language | NS-AIG-03 | UC-AIG-03 | MEASURE 2.11
AIA-01-11 | AI-01 | Incident response | Medium | Medium | Low | No AI-specific incident path exists yet. | Adopt the AI incident playbook; train agents and supervisors; include the vendor contact. | AI-01-G02;AI-01-G08 | Time to suspend in drills | NS-AIG-03 | UC-AIG-03 | MANAGE 2.3;MANAGE 4.3;GOVERN 4.3
AIA-02-01 | AI-02 | Intended purpose and affected people | Medium | Medium | Medium | Employees in Risk, Compliance, Finance and Legal rely on summaries; customers and counterparties named in documents are indirectly affected. | Defined permitted document types; summaries marked as AI-generated. |  | Use by document type | NS-AIG-01 | UC-AIG-01 | MAP 1.1;MAP 3.2;MAP 5.1
AIA-02-02 | AI-02 | Business criticality and fallback | Low | Low | Low | A convenience tool; staff can read the source documents. | None beyond fallback to reading the document. |  | Tool usage | NS-AIG-01 | UC-AIG-01 | MAP 1.4;MANAGE 2.4
AIA-02-03 | AI-02 | Data categories, privacy and confidentiality | High | High | Medium | Policies, contracts and board papers can contain confidential and personal information and legally privileged content. The document-upload tier's retention and training terms are unknown. | Classification gate: only Internal and permitted Confidential documents; exclude board papers, privileged and Restricted documents; contract confirms no training use and defined retention for document upload; privacy impact assessment. | AI-02-G02;AI-02-G05 | Documents uploaded by classification; privacy incidents | NS-AIG-01 | UC-AIG-01 | MEASURE 2.10;GOVERN 1.1
AIA-02-04 | AI-02 | Output reliability and hallucination | High | High | Medium | Summaries can omit or distort a clause that matters for a compliance decision. | Every answer cites the source passage; users must open the cited passage for any decision; periodic accuracy test on a policy set. | AI-02-G06 | Accuracy on a test set; user-reported errors | NS-AIG-03 | UC-AIG-03 | MEASURE 2.5;MEASURE 2.3;MAP 2.2
AIA-02-05 | AI-02 | Human oversight | High | High | Medium | The intake relies on users to verify summaries 'with no technical control proposed', which is not a control. | Technical traceability (source passage shown), required acknowledgement before copying output into a record, training. | AI-02-G04 | Share of outputs with source passage opened | NS-AIG-02 | UC-AIG-02 | MAP 3.5;GOVERN 3.2
AIA-02-06 | AI-02 | Security: prompt injection and data leakage | High | High | Medium | Uploaded documents can contain hidden instructions (indirect prompt injection), and without per-user access control one user could see another's documents. | Per-user document isolation; users can upload only what they may access; scanning of documents; no tool actions for the model; injection tests. | AI-02-G03 | Isolation test results | NS-AIG-01 | UC-AIG-01 | MEASURE 2.7
AIA-02-07 | AI-02 | Supplier and subprocessor dependency | High | High | Medium | The same vendor, but the document-upload tier is outside the evidence Northstar holds. Project 3 restricts V-03 from this use. | Close all Project 3 conditions and obtain written terms for the upload tier, or choose a different provider or a self-hosted option. | AI-02-G01 | Open Project 3 issues for V-03 | NS-SUP-01 | UC-SUP-01 | GOVERN 6.1;MAP 4.1;MANAGE 3.1
AIA-02-08 | AI-02 | Logging and traceability | Medium | High | Low | No record would show who uploaded which document or who saw which output. | Log uploader, document id and classification, query and answer; review access monthly. | AI-02-G07 | Log completeness check | NS-AIG-03 | UC-AIG-03 | MEASURE 2.8;MANAGE 4.1
AIA-02-09 | AI-02 | Change management (model and vendor changes) | Medium | Medium | Low | Vendor changes to upload processing could change retention without notice. | Notice-of-change clause; re-assess on any change. |  | Change notices | NS-AIG-03 | UC-AIG-03 | MANAGE 4.2;MEASURE 2.4
AIA-02-10 | AI-02 | Accessibility and fairness | Low | Low | Low | Few affected individuals; no decisions about people are made. | Prohibit use for employee or customer decisions. |  | Policy exceptions requested | NS-AIG-03 | UC-AIG-03 | MEASURE 2.11
AIA-02-11 | AI-02 | Incident response | High | High | Medium | Exposure of uploaded confidential documents to a third party is hard to reverse and to scope. | Adopt the AI incident playbook; contract right to deletion confirmation; evidence of what was uploaded from logs. | AI-02-G08 | Time to identify all documents uploaded in a drill | NS-AIG-03 | UC-AIG-03 | MANAGE 2.3;MANAGE 4.3;GOVERN 4.3

## Risk register
SIMULATED: fictional company, synthetic data, no real audit.
risk_id | use_case_id | risk_area | risk_statement | inherent | residual_as_proposed | target_residual | treatment | owner_role | linked_enterprise_risk | gates | status
AI-R01 | AI-01 | Intended purpose and affected people | Customers receive replies drafted by AI. Business customers could act on wrong information, but every reply is meant to be sent by an agent. | Medium | Medium | Low | Approved-content retrieval only; agent sends every reply. | Head of Customer Support | R-08 |  | Open until gates closed
AI-R02 | AI-01 | Business criticality and fallback | Support is customer-facing but a manual process exists, so the service can run without the tool. | Medium | Medium | Low | Documented manual fallback; ability to disable the tool within one hour. | Head of Customer Support | R-08 |  | Open until gates closed
AI-R03 | AI-01 | Data categories, privacy and confidentiality | Ticket text and account identifiers (Confidential personal and account information) go to a third-party model hosted in the United States (assumed) under unclear retention terms. | High | High | Medium | Redact identifiers before sending where possible; contract states retention and no training use for the API tier; privacy impact assessment (NS-PRV-01) including cross-border handling. | Head of Customer Support | R-09 | AI-01-G03 | Open until gates closed
AI-R04 | AI-01 | Output reliability and hallucination | Generated text can be fluent and wrong. A wrong answer about fees, deadlines or service status could harm a customer. | High | High | Medium | Answers limited to retrieved approved articles with the source article cited; pre-deployment evaluation on a representative ticket set; sampled quality review in operation. | Head of Customer Support | R-08 | AI-01-G05 | Open until gates closed
AI-R05 | AI-01 | Human oversight | The intake proposes agent review of every reply, but no technical control stops a send without review, and agents may approve routinely (automation bias). | High | Medium | Low | Send blocked until the agent approves in the tool; agent training; edit rate and rubber-stamp rate tracked (NS-AIG-02). | Head of Customer Support | R-08 | AI-01-G04 | Open until gates closed
AI-R06 | AI-01 | Security: prompt injection and data leakage | Customer ticket text is untrusted input and can contain instructions aimed at the model (prompt injection). Retrieved content or other customers' data could be exposed. | High | High | Medium | Retrieval limited to approved articles; no tool or system actions available to the model; output filtering; red-team tests with injection strings before launch. | Head of Customer Support | R-09 | AI-01-G06 | Open until gates closed
AI-R07 | AI-01 | Supplier and subprocessor dependency | Lumenvale AI Ltd. (V-03) has unclear retention, model training, subprocessor and incident terms and High residual risk in Project 3. | High | High | Medium | Close the Project 3 conditions for the API tier before go-live; exit plan to revert to manual drafting. | Head of Customer Support | R-09 | AI-01-G01 | Open until gates closed
AI-R08 | AI-01 | Logging and traceability | Without logs, an incorrect reply cannot be traced to its prompt, source articles and approving agent. | Medium | Medium | Low | Log prompt, retrieved article ids, draft, final reply and approver, retained for a stated period (proposed 90 days). | Head of Customer Support | R-08 | AI-01-G07 | Open until gates closed
AI-R09 | AI-01 | Change management (model and vendor changes) | A silent model or vendor change can alter behaviour or data handling. | Medium | Medium | Low | Pin the model version where offered; vendor must give notice of model and terms changes; re-run the evaluation set after any change. | Head of Customer Support | R-08 |  | Open until gates closed
AI-R10 | AI-01 | Accessibility and fairness | Tone and clarity may differ for customers who write in non-standard English or in French, and replies must be accessible. | Medium | Medium | Low | Evaluate on a mix of writing styles and languages; agents can rewrite freely. | Head of Customer Support | R-08 |  | Open until gates closed
AI-R11 | AI-01 | Incident response | No AI-specific incident path exists yet. | Medium | Medium | Low | Adopt the AI incident playbook; train agents and supervisors; include the vendor contact. | Head of Customer Support | R-08 | AI-01-G02;AI-01-G08 | Open until gates closed
AI-R12 | AI-02 | Intended purpose and affected people | Employees in Risk, Compliance, Finance and Legal rely on summaries; customers and counterparties named in documents are indirectly affected. | Medium | Medium | Medium | Defined permitted document types; summaries marked as AI-generated. | Chief Financial Officer | R-08 |  | Open until gates closed
AI-R13 | AI-02 | Business criticality and fallback | A convenience tool; staff can read the source documents. | Low | Low | Low | None beyond fallback to reading the document. | Chief Financial Officer | R-08 |  | Open until gates closed
AI-R14 | AI-02 | Data categories, privacy and confidentiality | Policies, contracts and board papers can contain confidential and personal information and legally privileged content. The document-upload tier's retention and training terms are unknown. | High | High | Medium | Classification gate: only Internal and permitted Confidential documents; exclude board papers, privileged and Restricted documents; contract confirms no training use and defined retention for document upload; privacy impact assessment. | Chief Financial Officer | R-09 | AI-02-G02;AI-02-G05 | Open until gates closed
AI-R15 | AI-02 | Output reliability and hallucination | Summaries can omit or distort a clause that matters for a compliance decision. | High | High | Medium | Every answer cites the source passage; users must open the cited passage for any decision; periodic accuracy test on a policy set. | Chief Financial Officer | R-08 | AI-02-G06 | Open until gates closed
AI-R16 | AI-02 | Human oversight | The intake relies on users to verify summaries 'with no technical control proposed', which is not a control. | High | High | Medium | Technical traceability (source passage shown), required acknowledgement before copying output into a record, training. | Chief Financial Officer | R-08 | AI-02-G04 | Open until gates closed
AI-R17 | AI-02 | Security: prompt injection and data leakage | Uploaded documents can contain hidden instructions (indirect prompt injection), and without per-user access control one user could see another's documents. | High | High | Medium | Per-user document isolation; users can upload only what they may access; scanning of documents; no tool actions for the model; injection tests. | Chief Financial Officer | R-09 | AI-02-G03 | Open until gates closed
AI-R18 | AI-02 | Supplier and subprocessor dependency | The same vendor, but the document-upload tier is outside the evidence Northstar holds. Project 3 restricts V-03 from this use. | High | High | Medium | Close all Project 3 conditions and obtain written terms for the upload tier, or choose a different provider or a self-hosted option. | Chief Financial Officer | R-09 | AI-02-G01 | Open until gates closed
AI-R19 | AI-02 | Logging and traceability | No record would show who uploaded which document or who saw which output. | Medium | High | Low | Log uploader, document id and classification, query and answer; review access monthly. | Chief Financial Officer | R-08 | AI-02-G07 | Open until gates closed
AI-R20 | AI-02 | Change management (model and vendor changes) | Vendor changes to upload processing could change retention without notice. | Medium | Medium | Low | Notice-of-change clause; re-assess on any change. | Chief Financial Officer | R-08 |  | Open until gates closed
AI-R21 | AI-02 | Accessibility and fairness | Few affected individuals; no decisions about people are made. | Low | Low | Low | Prohibit use for employee or customer decisions. | Chief Financial Officer | R-08 |  | Open until gates closed
AI-R22 | AI-02 | Incident response | Exposure of uploaded confidential documents to a third party is hard to reverse and to scope. | High | High | Medium | Adopt the AI incident playbook; contract right to deletion confirmation; evidence of what was uploaded from logs. | Chief Financial Officer | R-08 | AI-02-G08 | Open until gates closed

## Gates
SIMULATED: fictional company, synthetic data, no real audit.
gate_id | use_case_id | requirement | owner_role | evidence_to_close | risk_area | target_date | status | status_basis
AI-01-G01 | AI-01 | Written confirmation from Lumenvale of prompt and output retention, no model training on Northstar content, and a subprocessor list, for the API tier | Chief Product Officer | Signed terms and the subprocessor list on file | Supplier and subprocessor dependency | 2026-11-01 | Blocked by 3 open vendor issue(s) in Project 3 | Status read from remediation-and-monitoring-tracker.csv
AI-01-G02 | AI-01 | Incident notification clause with a stated time limit, content and named contact | Head of Procurement | Amended agreement | Incident response | 2026-11-01 | Blocked by 1 open vendor issue(s) in Project 3 | Status read from remediation-and-monitoring-tracker.csv
AI-01-G03 | AI-01 | Privacy impact assessment completed, including cross-border handling and redaction of identifiers | Privacy Officer | Approved assessment | Data categories, privacy and confidentiality | 2026-11-15 | In progress | Scenario status
AI-01-G04 | AI-01 | Technical enforcement that no reply is sent without agent approval | Head of Customer Support | Configuration evidence and a passed test | Human oversight | 2026-11-15 | Not started | Scenario status
AI-01-G05 | AI-01 | Pre-deployment evaluation on a representative ticket set with documented thresholds met (material error rate at or below 2%) | Head of Customer Support | Evaluation report with test set, method and results | Output reliability and hallucination | 2026-11-15 | In progress | Scenario status
AI-01-G06 | AI-01 | Prompt injection and data leakage tests passed | IT Security Manager | Test report | Security: prompt injection and data leakage | 2026-11-15 | Not started | Scenario status
AI-01-G07 | AI-01 | Logging of prompt, sources, draft, final reply and approver in place with a retention period | Head of Platform Engineering | Log sample and retention configuration | Logging and traceability | 2026-11-22 | Not started | Scenario status
AI-01-G08 | AI-01 | Monitoring plan live and the AI incident playbook rehearsed with support supervisors | AI Governance Committee | First monitoring report and drill record | Incident response | 2026-11-22 | Not started | Scenario status
AI-02-G01 | AI-02 | Written terms for the document-upload tier: retention, no model training, subprocessors, incident notification; or an alternative provider | Chief Financial Officer | Signed terms or a new vendor assessment | Supplier and subprocessor dependency | 2027-01-31 | Blocked by 3 open vendor issue(s) in Project 3 | Status read from remediation-and-monitoring-tracker.csv
AI-02-G02 | AI-02 | Classification gate that blocks upload of board papers, privileged and Restricted documents | Head of Platform Engineering | Configuration evidence and a passed test | Data categories, privacy and confidentiality | 2027-01-31 | Not started | Scenario status
AI-02-G03 | AI-02 | Per-user document isolation and upload limited to documents the user may access | Head of Platform Engineering | Isolation test report | Security: prompt injection and data leakage | 2027-01-31 | Not started | Scenario status
AI-02-G04 | AI-02 | Technical traceability: every answer shows the source passage and requires acknowledgement before reuse in a record | Chief Financial Officer | Demonstration and test | Human oversight | 2027-01-31 | Not started | Scenario status
AI-02-G05 | AI-02 | Privacy impact assessment and legal review of privilege and confidentiality risks | Privacy Officer | Approved assessment and legal sign-off | Data categories, privacy and confidentiality | 2027-01-31 | Not started | Scenario status
AI-02-G06 | AI-02 | Accuracy evaluation on a representative set of policy documents with documented thresholds | Chief Financial Officer | Evaluation report | Output reliability and hallucination | 2027-02-28 | Not started | Scenario status
AI-02-G07 | AI-02 | Upload and access logging with monthly access review | IT Security Manager | Log sample and review record | Logging and traceability | 2027-02-28 | Not started | Scenario status
AI-02-G08 | AI-02 | Monitoring plan and AI incident playbook adopted and rehearsed | AI Governance Committee | Monitoring report and drill record | Incident response | 2027-02-28 | Not started | Scenario status

## Control mapping
SIMULATED: fictional company, synthetic data, no real audit.
risk_area | use_case_id | northstar_control | unified_control | framework | reference | intent | verification | confidence | note
Intended purpose and affected people | AI-01 | NS-AIG-01 | UC-AIG-01 | NIST AI RMF 1.0 | MAP 1.1 | Intended purposes, context and deployment settings are documented | verified (primary: NIST AI 100-1) | Medium | Judgement that the control supports the outcome; not evidence of conformance.
Intended purpose and affected people | AI-01 | NS-AIG-01 | UC-AIG-01 | NIST AI RMF 1.0 | MAP 3.2 | Costs of AI errors are examined | verified (primary: NIST AI 100-1) | Medium | Judgement that the control supports the outcome; not evidence of conformance.
Intended purpose and affected people | AI-01 | NS-AIG-01 | UC-AIG-01 | NIST AI RMF 1.0 | MAP 5.1 | Likelihood and magnitude of impacts are identified | verified (primary: NIST AI 100-1) | Medium | Judgement that the control supports the outcome; not evidence of conformance.
Business criticality and fallback | AI-01 | NS-AIG-01 | UC-AIG-01 | NIST AI RMF 1.0 | MAP 1.4 | Business value and context of use are defined | verified (primary: NIST AI 100-1) | Medium | Judgement that the control supports the outcome; not evidence of conformance.
Business criticality and fallback | AI-01 | NS-AIG-01 | UC-AIG-01 | NIST AI RMF 1.0 | MANAGE 2.4 | Mechanisms exist to supersede, disengage or deactivate the system | verified (primary: NIST AI 100-1) | Medium | Judgement that the control supports the outcome; not evidence of conformance.
Data categories, privacy and confidentiality | AI-01 | NS-AIG-01 | UC-AIG-01 | NIST AI RMF 1.0 | MEASURE 2.10 | Privacy risk is examined | verified (primary: NIST AI 100-1) | Medium | Judgement that the control supports the outcome; not evidence of conformance.
Data categories, privacy and confidentiality | AI-01 | NS-AIG-01 | UC-AIG-01 | NIST AI RMF 1.0 | GOVERN 1.1 | Legal and regulatory requirements involving AI are understood and documented | verified (primary: NIST AI 100-1) | Medium | Judgement that the control supports the outcome; not evidence of conformance.
Output reliability and hallucination | AI-01 | NS-AIG-03 | UC-AIG-03 | NIST AI RMF 1.0 | MEASURE 2.5 | The system is shown to be valid and reliable, with limits documented | verified (primary: NIST AI 100-1) | Medium | Judgement that the control supports the outcome; not evidence of conformance.
Output reliability and hallucination | AI-01 | NS-AIG-03 | UC-AIG-03 | NIST AI RMF 1.0 | MEASURE 2.3 | Performance is measured against criteria | verified (primary: NIST AI 100-1) | Medium | Judgement that the control supports the outcome; not evidence of conformance.
Output reliability and hallucination | AI-01 | NS-AIG-03 | UC-AIG-03 | NIST AI RMF 1.0 | MAP 2.2 | Knowledge limits and human oversight of outputs are documented | verified (primary: NIST AI 100-1) | Medium | Judgement that the control supports the outcome; not evidence of conformance.
Human oversight | AI-01 | NS-AIG-02 | UC-AIG-02 | NIST AI RMF 1.0 | MAP 3.5 | Human oversight processes are defined and documented | verified (primary: NIST AI 100-1) | Medium | Judgement that the control supports the outcome; not evidence of conformance.
Human oversight | AI-01 | NS-AIG-02 | UC-AIG-02 | NIST AI RMF 1.0 | GOVERN 3.2 | Roles for human-AI configurations and oversight are defined | verified (primary: NIST AI 100-1) | Medium | Judgement that the control supports the outcome; not evidence of conformance.
Security: prompt injection and data leakage | AI-01 | NS-AIG-01 | UC-AIG-01 | NIST AI RMF 1.0 | MEASURE 2.7 | Security and resilience are evaluated | verified (primary: NIST AI 100-1) | Medium | Judgement that the control supports the outcome; not evidence of conformance.
Supplier and subprocessor dependency | AI-01 | NS-SUP-01 | UC-SUP-01 | NIST AI RMF 1.0 | GOVERN 6.1 | Policies address AI risks from third parties | verified (primary: NIST AI 100-1) | Medium | Judgement that the control supports the outcome; not evidence of conformance.
Supplier and subprocessor dependency | AI-01 | NS-SUP-01 | UC-SUP-01 | NIST AI RMF 1.0 | MAP 4.1 | Risks of third-party components are mapped | verified (primary: NIST AI 100-1) | Medium | Judgement that the control supports the outcome; not evidence of conformance.
Supplier and subprocessor dependency | AI-01 | NS-SUP-01 | UC-SUP-01 | NIST AI RMF 1.0 | MANAGE 3.1 | Third-party AI risks are monitored and controls applied | verified (primary: NIST AI 100-1) | Medium | Judgement that the control supports the outcome; not evidence of conformance.
Logging and traceability | AI-01 | NS-AIG-03 | UC-AIG-03 | NIST AI RMF 1.0 | MEASURE 2.8 | Transparency and accountability risks are examined | verified (primary: NIST AI 100-1) | Medium | Judgement that the control supports the outcome; not evidence of conformance.
Logging and traceability | AI-01 | NS-AIG-03 | UC-AIG-03 | NIST AI RMF 1.0 | MANAGE 4.1 | Post-deployment monitoring plans are implemented | verified (primary: NIST AI 100-1) | Medium | Judgement that the control supports the outcome; not evidence of conformance.
Change management (model and vendor changes) | AI-01 | NS-AIG-03 | UC-AIG-03 | NIST AI RMF 1.0 | MANAGE 4.2 | Continual improvement is built into updates | verified (primary: NIST AI 100-1) | Medium | Judgement that the control supports the outcome; not evidence of conformance.
Change management (model and vendor changes) | AI-01 | NS-AIG-03 | UC-AIG-03 | NIST AI RMF 1.0 | MEASURE 2.4 | Behaviour is monitored in production | verified (primary: NIST AI 100-1) | Medium | Judgement that the control supports the outcome; not evidence of conformance.
Accessibility and fairness | AI-01 | NS-AIG-03 | UC-AIG-03 | NIST AI RMF 1.0 | MEASURE 2.11 | Fairness and bias are evaluated | verified (primary: NIST AI 100-1) | Medium | Judgement that the control supports the outcome; not evidence of conformance.
Incident response | AI-01 | NS-AIG-03 | UC-AIG-03 | NIST AI RMF 1.0 | MANAGE 2.3 | Procedures exist to respond to and recover from newly identified risks | verified (primary: NIST AI 100-1) | Medium | Judgement that the control supports the outcome; not evidence of conformance.
Incident response | AI-01 | NS-AIG-03 | UC-AIG-03 | NIST AI RMF 1.0 | MANAGE 4.3 | Incidents and errors are communicated and tracked | verified (primary: NIST AI 100-1) | Medium | Judgement that the control supports the outcome; not evidence of conformance.
Incident response | AI-01 | NS-AIG-03 | UC-AIG-03 | NIST AI RMF 1.0 | GOVERN 4.3 | Practices enable AI testing, incident identification and information sharing | verified (primary: NIST AI 100-1) | Medium | Judgement that the control supports the outcome; not evidence of conformance.
Intended purpose and affected people | AI-02 | NS-AIG-01 | UC-AIG-01 | NIST AI RMF 1.0 | MAP 1.1 | Intended purposes, context and deployment settings are documented | verified (primary: NIST AI 100-1) | Medium | Judgement that the control supports the outcome; not evidence of conformance.
Intended purpose and affected people | AI-02 | NS-AIG-01 | UC-AIG-01 | NIST AI RMF 1.0 | MAP 3.2 | Costs of AI errors are examined | verified (primary: NIST AI 100-1) | Medium | Judgement that the control supports the outcome; not evidence of conformance.
Intended purpose and affected people | AI-02 | NS-AIG-01 | UC-AIG-01 | NIST AI RMF 1.0 | MAP 5.1 | Likelihood and magnitude of impacts are identified | verified (primary: NIST AI 100-1) | Medium | Judgement that the control supports the outcome; not evidence of conformance.
Business criticality and fallback | AI-02 | NS-AIG-01 | UC-AIG-01 | NIST AI RMF 1.0 | MAP 1.4 | Business value and context of use are defined | verified (primary: NIST AI 100-1) | Medium | Judgement that the control supports the outcome; not evidence of conformance.
Business criticality and fallback | AI-02 | NS-AIG-01 | UC-AIG-01 | NIST AI RMF 1.0 | MANAGE 2.4 | Mechanisms exist to supersede, disengage or deactivate the system | verified (primary: NIST AI 100-1) | Medium | Judgement that the control supports the outcome; not evidence of conformance.
Data categories, privacy and confidentiality | AI-02 | NS-AIG-01 | UC-AIG-01 | NIST AI RMF 1.0 | MEASURE 2.10 | Privacy risk is examined | verified (primary: NIST AI 100-1) | Medium | Judgement that the control supports the outcome; not evidence of conformance.
Data categories, privacy and confidentiality | AI-02 | NS-AIG-01 | UC-AIG-01 | NIST AI RMF 1.0 | GOVERN 1.1 | Legal and regulatory requirements involving AI are understood and documented | verified (primary: NIST AI 100-1) | Medium | Judgement that the control supports the outcome; not evidence of conformance.
Output reliability and hallucination | AI-02 | NS-AIG-03 | UC-AIG-03 | NIST AI RMF 1.0 | MEASURE 2.5 | The system is shown to be valid and reliable, with limits documented | verified (primary: NIST AI 100-1) | Medium | Judgement that the control supports the outcome; not evidence of conformance.
Output reliability and hallucination | AI-02 | NS-AIG-03 | UC-AIG-03 | NIST AI RMF 1.0 | MEASURE 2.3 | Performance is measured against criteria | verified (primary: NIST AI 100-1) | Medium | Judgement that the control supports the outcome; not evidence of conformance.
Output reliability and hallucination | AI-02 | NS-AIG-03 | UC-AIG-03 | NIST AI RMF 1.0 | MAP 2.2 | Knowledge limits and human oversight of outputs are documented | verified (primary: NIST AI 100-1) | Medium | Judgement that the control supports the outcome; not evidence of conformance.
Human oversight | AI-02 | NS-AIG-02 | UC-AIG-02 | NIST AI RMF 1.0 | MAP 3.5 | Human oversight processes are defined and documented | verified (primary: NIST AI 100-1) | Medium | Judgement that the control supports the outcome; not evidence of conformance.
Human oversight | AI-02 | NS-AIG-02 | UC-AIG-02 | NIST AI RMF 1.0 | GOVERN 3.2 | Roles for human-AI configurations and oversight are defined | verified (primary: NIST AI 100-1) | Medium | Judgement that the control supports the outcome; not evidence of conformance.
Security: prompt injection and data leakage | AI-02 | NS-AIG-01 | UC-AIG-01 | NIST AI RMF 1.0 | MEASURE 2.7 | Security and resilience are evaluated | verified (primary: NIST AI 100-1) | Medium | Judgement that the control supports the outcome; not evidence of conformance.
Supplier and subprocessor dependency | AI-02 | NS-SUP-01 | UC-SUP-01 | NIST AI RMF 1.0 | GOVERN 6.1 | Policies address AI risks from third parties | verified (primary: NIST AI 100-1) | Medium | Judgement that the control supports the outcome; not evidence of conformance.
Supplier and subprocessor dependency | AI-02 | NS-SUP-01 | UC-SUP-01 | NIST AI RMF 1.0 | MAP 4.1 | Risks of third-party components are mapped | verified (primary: NIST AI 100-1) | Medium | Judgement that the control supports the outcome; not evidence of conformance.
Supplier and subprocessor dependency | AI-02 | NS-SUP-01 | UC-SUP-01 | NIST AI RMF 1.0 | MANAGE 3.1 | Third-party AI risks are monitored and controls applied | verified (primary: NIST AI 100-1) | Medium | Judgement that the control supports the outcome; not evidence of conformance.
Logging and traceability | AI-02 | NS-AIG-03 | UC-AIG-03 | NIST AI RMF 1.0 | MEASURE 2.8 | Transparency and accountability risks are examined | verified (primary: NIST AI 100-1) | Medium | Judgement that the control supports the outcome; not evidence of conformance.
Logging and traceability | AI-02 | NS-AIG-03 | UC-AIG-03 | NIST AI RMF 1.0 | MANAGE 4.1 | Post-deployment monitoring plans are implemented | verified (primary: NIST AI 100-1) | Medium | Judgement that the control supports the outcome; not evidence of conformance.
Change management (model and vendor changes) | AI-02 | NS-AIG-03 | UC-AIG-03 | NIST AI RMF 1.0 | MANAGE 4.2 | Continual improvement is built into updates | verified (primary: NIST AI 100-1) | Medium | Judgement that the control supports the outcome; not evidence of conformance.
Change management (model and vendor changes) | AI-02 | NS-AIG-03 | UC-AIG-03 | NIST AI RMF 1.0 | MEASURE 2.4 | Behaviour is monitored in production | verified (primary: NIST AI 100-1) | Medium | Judgement that the control supports the outcome; not evidence of conformance.
Accessibility and fairness | AI-02 | NS-AIG-03 | UC-AIG-03 | NIST AI RMF 1.0 | MEASURE 2.11 | Fairness and bias are evaluated | verified (primary: NIST AI 100-1) | Medium | Judgement that the control supports the outcome; not evidence of conformance.
Incident response | AI-02 | NS-AIG-03 | UC-AIG-03 | NIST AI RMF 1.0 | MANAGE 2.3 | Procedures exist to respond to and recover from newly identified risks | verified (primary: NIST AI 100-1) | Medium | Judgement that the control supports the outcome; not evidence of conformance.
Incident response | AI-02 | NS-AIG-03 | UC-AIG-03 | NIST AI RMF 1.0 | MANAGE 4.3 | Incidents and errors are communicated and tracked | verified (primary: NIST AI 100-1) | Medium | Judgement that the control supports the outcome; not evidence of conformance.
Incident response | AI-02 | NS-AIG-03 | UC-AIG-03 | NIST AI RMF 1.0 | GOVERN 4.3 | Practices enable AI testing, incident identification and information sharing | verified (primary: NIST AI 100-1) | Medium | Judgement that the control supports the outcome; not evidence of conformance.
Whole programme | AI-01 | NS-AIG-01 to NS-AIG-03 | UC-AIG-01 to UC-AIG-03 | ISO/IEC 42001:2023 | Management-system level only | A management system standard for establishing, implementing, maintaining and improving an AI management system (source S008 abstract) | partially verified (abstract only; standard text not read) | Low | No clause-level mapping is made. The governance programme resembles a management system but nothing here claims alignment, readiness or certification.
Whole programme | AI-02 | NS-AIG-01 to NS-AIG-03 | UC-AIG-01 to UC-AIG-03 | ISO/IEC 42001:2023 | Management-system level only | A management system standard for establishing, implementing, maintaining and improving an AI management system (source S008 abstract) | partially verified (abstract only; standard text not read) | Low | No clause-level mapping is made. The governance programme resembles a management system but nothing here claims alignment, readiness or certification.

## Monitoring
SIMULATED: fictional company, synthetic data, no real audit.
use_case_id | measure | definition | amber_threshold | red_threshold_action | frequency | owner_role | threshold_basis
AI-01 | Material error rate | Share of sampled drafts with a factual error that would mislead a customer, from a weekly 50-draft review | More than 1% | More than 2%: suspend | Weekly for 8 weeks, then monthly | Head of Customer Support | Proposed starting value; calibrate on the pilot baseline. Not derived from data.
AI-01 | Human edit rate | Share of drafts the agent edited before sending | Below 5% (possible rubber-stamping) or above 60% (poor quality) | Below 2% for two weeks: pause and retrain | Weekly | Head of Customer Support | Proposed starting value; calibrate on the pilot baseline. Not derived from data.
AI-01 | Privacy or security incidents | Confirmed exposure of personal or confidential data, or successful prompt injection | Any near miss | Any confirmed incident: suspend | Per event | IT Security Manager | Proposed starting value; calibrate on the pilot baseline. Not derived from data.
AI-01 | Customer complaints | Complaints that cite an AI-drafted reply | 2 in a month | 5 in a month: review for suspension | Monthly | Head of Customer Support | Proposed starting value; calibrate on the pilot baseline. Not derived from data.
AI-01 | Drift and change triggers | Model version change, vendor terms change, knowledge-base major update | Any change notice | Change without re-test: suspend | Per event | Head of Platform Engineering | Proposed starting value; calibrate on the pilot baseline. Not derived from data.
AI-01 | Vendor issues | Open Project 3 issues for V-03 and their aging | Any overdue High issue | Overdue over 30 days: escalate to the Chief Risk Officer | Monthly | Head of Procurement | Proposed starting value; calibrate on the pilot baseline. Not derived from data.
AI-02 | Documents by classification | Uploaded documents by classification label | Any Confidential upload without exemption | Any Restricted or privileged upload: suspend | Weekly (after approval) | Chief Financial Officer | Proposed starting value; calibrate on the pilot baseline. Not derived from data.
AI-02 | Accuracy on test set | Share of answers matching the source on a quarterly policy test set | Below 95% | Below 90%: suspend | Quarterly | Chief Financial Officer | Proposed starting value; calibrate on the pilot baseline. Not derived from data.
AI-02 | Source-passage opened | Share of answers where the user opened the cited passage | Below 60% | Below 30%: review | Monthly | AI Governance Committee | Proposed starting value; calibrate on the pilot baseline. Not derived from data.
AI-02 | Privacy or security incidents | Confirmed exposure or isolation failure | Any near miss | Any confirmed incident: suspend | Per event | IT Security Manager | Proposed starting value; calibrate on the pilot baseline. Not derived from data.

## Supplier checklist
SIMULATED: fictional company, synthetic data, no real audit.
item_id | topic | requirement | project3_area | lumenvale_status_from_project3 | meets_requirement | note
AIS-01 | Retention | Retention period for prompts, outputs and uploaded documents, by tier and feature | Retention and deletion | Unclear term | No | Vendor questionnaire answers are self-reported and do not count as independent verification.
AIS-02 | Model training | No use of customer content to train or improve models, in every tier and feature | Model training and data use | Unclear term | No | Vendor questionnaire answers are self-reported and do not count as independent verification.
AIS-03 | Subprocessors | Subprocessor list with hosting regions and change notice | Subcontractors and subprocessors | Not provided | No | Vendor questionnaire answers are self-reported and do not count as independent verification.
AIS-04 | Incident notification | Time-limited notification clause with content and named contact | Incident notification | Unclear term | No | Vendor questionnaire answers are self-reported and do not count as independent verification.
AIS-05 | Assurance | Independent report covering operating effectiveness over a period (SOC 2 Type II or equivalent) | Independent assurance report | Verified with exception or limitation | No | Vendor questionnaire answers are self-reported and do not count as independent verification.
AIS-06 | Access control | Staff access to customer content restricted, logged and reviewed | Access control | Self-reported | No | Vendor questionnaire answers are self-reported and do not count as independent verification.
AIS-07 | Encryption | Encryption at rest and in transit and key management | Encryption | Self-reported | No | Vendor questionnaire answers are self-reported and do not count as independent verification.
AIS-08 | Penetration testing | Independent test summary including prompt injection and tenant isolation | Penetration testing | Not provided | No | Vendor questionnaire answers are self-reported and do not count as independent verification.
AIS-09 | Continuity | Availability commitment and recovery objectives | Business continuity and recovery | Not provided | No | Vendor questionnaire answers are self-reported and do not count as independent verification.
AIS-10 | Tenant isolation | How one customer's content is kept from another's, including retrieval indexes |  | Not assessed in Project 3 | Unknown | Vendor questionnaire answers are self-reported and do not count as independent verification.
AIS-11 | Output filtering | Controls for harmful or leaking output and customer-configurable guardrails |  | Not assessed in Project 3 | Unknown | Vendor questionnaire answers are self-reported and do not count as independent verification.
AIS-12 | Model change notice | Advance notice of model version, policy or behaviour changes |  | Not assessed in Project 3 | Unknown | Vendor questionnaire answers are self-reported and do not count as independent verification.
AIS-13 | Region control | Ability to restrict processing and storage to Canada |  | Not assessed in Project 3 | Unknown | Vendor questionnaire answers are self-reported and do not count as independent verification.
AIS-14 | Deletion on exit | Deletion of content and indexes at termination with written confirmation |  | Not assessed in Project 3 | Unknown | Vendor questionnaire answers are self-reported and do not count as independent verification.