## Read me
SIMULATED: fictional company, synthetic data, no real audit.
Workbook: finding-register. Generated by the scripts listed in docs/artifact-index.md from the shared synthetic datasets.
On every sheet the header is row 2, headers are frozen, and filters are on. Empty cells mean no value.
Columns such as status, severity or decision have a drop-down list of the values currently in use; extend the list if you add a new value.
Dates are ISO 8601 (YYYY-MM-DD). Nothing here is client data or an assurance opinion.
Sheets:
Findings: 14 rows, 20 columns
Management action plan: 16 rows, 12 columns
Exceptions: 71 rows, 5 columns
Retest evidence: 11 rows, 5 columns

## Findings
SIMULATED: fictional company, synthetic data, no real audit.
finding_id | project_id | title | severity | issue_type | criteria_reference | condition | cause | consequence_or_risk | recommendation | owner_role | target_date | status | evidence_refs | test_ids | compensating_controls | response_type | management_response | closure_criteria | retest_status
F-01 | P1 | Terminated employees retained active access to in-scope systems | High | Operating failure | NS-IAM-02: access of terminated employees is removed within 2 business days (fictional Access Management Standard). | 8 of 35 leaver accounts (22.9%) were not removed in time. 4 accounts were still Active at the extract date, and 4 were disabled 7 to 15 business days after termination. A-0132 (SYS-02 Payments Console Admin) logged in 6 days after the employee's termination. The HR termination list supplied was partial (EV-002), so further exceptions may exist. | Offboarding depends on a manual notification from HR to IT; there is no automated deprovisioning from the HR feed, and the quarterly access reviews did not detect the remaining accounts (see F-03). | A former employee could reach Restricted payment or ledger data. This conflicts with Northstar's low appetite for unauthorised access to Restricted data; confirmed access after termination escalates to the Chief Risk Officer. | Disable the remaining accounts immediately; investigate the post-termination login to establish who used the account; automate deprovisioning from the HR termination feed and add a daily reconciliation of terminated employees to active accounts. | IT Security Manager | 2026-11-17 | Partially remediated | EV-001;EV-002 | T-02 | None relied on. The quarterly access review (NS-IAM-04) is the compensating detective control; it did not operate effectively (F-03), so no reliance is placed on it. | Agreed | We agree. The four active accounts have been escalated for immediate disablement and a security investigation of the post-termination login has been opened. HR-to-IT automation is planned for the Q4 release. | All leaver accounts disabled and re-tested on a fresh HR termination list; investigation report on the post-termination login approved by the Chief Risk Officer; evidence of the automated HR-to-IT reconciliation operating for one full month. | Retested 2026-09-28: partially remediated
F-02 | P1 | Administrator access granted without documented approval | High | Operating failure | NS-PAM-01: Admin-level access requires system owner approval and documented justification before it is granted. | 2 of 19 Admin accounts (10.5%) have no approval ticket, approver or approval date, on SYS-03, SYS-05. | Admin access can be granted directly in the administration console without a ticket reference check. | Unauthorised or excessive privileged access could exist undetected on systems holding Restricted data. | Obtain retrospective system-owner approval or remove the access; require a ticket reference before an Admin role can be assigned; add Admin accounts to the monthly privileged access report. | Head of Platform Engineering | 2026-11-17 | Remediation in progress | EV-001 | T-08 | None identified in the evidence provided. | Agreed | Agreed. Retrospective approvals will be sought by the target date; accounts without a valid business need will be removed. | Documented system-owner approval or removal for each Admin account without approval; ticket-reference enforcement shown in configuration evidence; Internal Audit re-performs the Admin population test. | Not yet due
F-03 | P1 | Quarterly user access reviews were late, incomplete, not independent or ineffective | High | Operating failure and design deficiency | NS-IAM-04: system owners review all accounts each quarter within 30 days of quarter end (design: no independence requirement). | 8 of 10 reviews failed at least one attribute: 1 not completed, 1 completed late, 1 reviewed by a user holding Admin access on the same system, 1 reviewed an incomplete population, and 4 attested as complete although terminated users' accounts remained Active. The control design does not require reviewer independence. | Reviews are run from spreadsheets without a completeness check, there is no escalation for overdue reviews, and the control text does not prohibit self-review. | The review is the detective control that should catch inappropriate access (including F-01); when it does not operate, inappropriate access persists. | Require reviewer independence in the control text; generate the review population from the system extract and reconcile it before attestation; escalate overdue reviews at day 30; include a leaver check in every review. | IT Security Manager | 2026-11-17 | Open | EV-014;EV-015;EV-016;EV-017;EV-018;EV-019;EV-020;EV-021 | T-04 | None relied on. | Agreed | Agreed. The control text will be revised for independence and a population reconciliation step added before the Q3 review. | Revised control text with an independence requirement; the next quarter's review evidenced as complete, on time, independent and reconciled to the system extract, with a leaver check. | Not yet due
F-04 | P1 | Service accounts without a valid owner | Medium | Design deficiency and operating failure | NS-IAM-05: each service account is assigned an owner when it is created (design: no recertification or reassignment). | 4 of 14 service accounts (28.6%) have no owner (3 with none recorded) or an owner who has left (1 with a terminated owner). The control records an owner only at creation, with no recertification. | Ownership is not revisited when owners leave; no register reconciliation exists. | Credentials of unowned service accounts may not be rotated or reviewed, increasing the chance of misuse going unnoticed. | Assign owners; add owner recertification to the quarterly review; trigger reassignment from the leaver process. | Head of Platform Engineering | 2026-12-17 | Open | EV-001 | T-05 | None identified. | Agreed | Agreed. | Owners assigned to every service account; owner recertification added to the quarterly review; test of the service-account population shows zero accounts without a current owner. | Not yet due
F-05 | P1 | Multi-factor authentication not enabled on some human accounts, including an administrator | High | Operating failure (isolated, but one Admin account) | NS-IAM-07: MFA is enforced through Corporate SSO for all human accounts on in-scope systems. | 3 of 413 human accounts (0.7%) have MFA disabled, including 1 Admin account. | These accounts authenticate locally on the system, bypassing Corporate SSO. | A stolen password alone could give access, including administrator access to source control and CI/CD. | Enable MFA on the three accounts; disable local authentication for human users; alert on accounts outside SSO. | IT Security Manager | 2026-11-17 | Closed (retested) | EV-001 | T-07 | Corporate SSO conditional access would compensate for SSO-routed accounts only; it does not cover these local accounts. | Agreed | Agreed. MFA enabled; local authentication to be disabled by the target date. | MFA flag verified enabled on the three accounts in the live console; local authentication for human users disabled (configuration evidence). | Retested 2026-09-28: remediated
F-06 | P1 | Dormant and role-change access not removed | Medium | Operating failure | NS-IAM-06: accounts idle over 90 days are disabled unless excepted. NS-IAM-03: access follows role changes within 30 days. | 4 human accounts of current employees were idle more than 90 days without an exception, and 2 movers kept access from their previous department more than 30 days after transfer. | The monthly dormant-account list is produced but not consistently actioned; movers are not part of the leaver trigger. | Unused access widens the attack surface; retained role access breaks least-privilege and segregation expectations. | Disable dormant accounts automatically after 90 days with a manager exception route; add a mover review to the transfer workflow. | IT Security Manager | 2026-12-17 | Remediation in progress | EV-001 | T-06;T-03 | Monthly dormant-account list exists but was not actioned; treated as not compensating. | Agreed with modification | We agree on the facts but rate the dormant-account condition Low, because the idle accounts hold Standard privilege. Internal Audit retains the Medium rating because one mover retains access to the Payments API and the dormant-account process failed repeatedly. | Dormant accounts disabled and a re-run of the idle-account test shows no unexcepted accounts over 90 days; mover access removed and a mover review step evidenced for the next two transfers. | Dormant accounts retested 2026-09-28: remediated; mover access not yet due
F-07 | P1 | Some access was granted before approval, or without an approval record | Low | Isolated exceptions | NS-IAM-01: access is provisioned only after documented approval by the requester's line manager. | 5 of 408 non-Admin accounts (1.2%) have no approval record (2) or an approval dated after the grant (3). Admin accounts are tested separately in T-08 and reported in F-02. | Approval is attached to the request ticket after provisioning in some cases; no automated check blocks provisioning without a ticket. | Access might not have been authorised when it was granted. Exception rate is within the 5% tolerance and none involves Admin access. | Require a ticket reference at provisioning; report accounts without a ticket monthly. | Head of IT Operations | 2027-01-16 | Risk accepted | EV-001 | T-01 | Monthly ticket-existence report proposed by management as the mitigating control; not yet operating, so no reliance. | Risk accepted | Residual risk is below the executive threshold and is accepted by the risk owner with the monthly ticket report as a mitigating control. | Not applicable (risk accepted). Accepted by the risk owner; revisit if the exception rate exceeds tolerance at the next audit. | Not applicable (risk accepted)
F-08 | P1 | Developers deployed their own changes to production | High | Operating failure | NS-CHG-03: the deployer of a Normal or Emergency change is not its developer. | 4 of 91 Normal and Emergency changes (4.4%) were deployed by their own developer, on SYS-01, SYS-02, SYS-03, SYS-05, including payment and ledger systems. | Deployment permissions in the pipeline are not separated from developer roles for some engineers. | Unreviewed code could reach production without a second person, enabling error or fraud in payment systems. | Technically enforce separation of developer and deployer roles in the pipeline; review pipeline permissions quarterly. | Head of Payments Engineering | 2026-11-17 | Open | EV-003 | T-11 | Peer review of code (NS-SDL-01) would compensate if it operated; it was not tested in this engagement, so no reliance is placed on it. | Agreed | Agreed. Pipeline role separation will be enforced; interim monitoring is in place. | Pipeline configuration shows developer and deployer roles are separated; a re-run of the deployer-versus-developer test over the next quarter has zero exceptions. | Not yet due
F-09 | P1 | Normal changes lacked test evidence, independent approval or prior approval | Medium | Operating failure | NS-CHG-01 and NS-CHG-02: independent approval before implementation; recorded Pass test result. | Of 77 Normal changes, 5 had no recorded test result, 2 were approved by their requester and 3 were approved after implementation. | The change tool allows closing a change without mandatory test and approval fields. | Defective or unauthorised changes might reach production, including the Payments API and Core Ledger. | Make test result, evidence reference and independent approver mandatory fields; block implementation without prior approval. | Change Manager | 2026-12-17 | Open | EV-003 | T-09;T-10 | None identified. | Agreed | Agreed. Field validation is in the tool backlog. | Mandatory test, evidence and independent approver fields live in the change tool; a re-test over the next quarter's Normal changes has zero exceptions. | Not yet due
F-10 | P1 | Emergency changes approved retrospectively after the 2-business-day limit | Medium | Operating failure | NS-CHG-04: retrospective approval within 2 business days. | 3 of 14 Emergency changes (21.4%) were approved 6 to 15 business days after implementation. All are on SYS-01. | No reminder or escalation is triggered when retrospective approval is outstanding. | Emergency changes remain unreviewed for weeks. | Automate reminders at day 1 and escalation at day 2. | Change Manager | 2026-12-17 | Open | EV-003 | T-12 | None identified. | Agreed | Agreed. | Automated day-1 reminder and day-2 escalation in operation; next quarter's Emergency changes all approved within 2 business days. | Not yet due
F-11 | P1 | Failed backups of the Payments API were not re-run | Medium | Operating failure | NS-OPS-01: failed jobs are re-run and any failure not resolved within 24 hours is escalated. | 5 failed backup jobs on SYS-02 (dates: 2026-02-03, 2026-03-17, 2026-05-11, 2026-05-12, 2026-05-13) have no successful re-run. No escalation records were provided. | The on-duty engineer is notified but there is no ticket or tracking for failed jobs. | Recovery points for the Payments API are missing for the affected dates, increasing potential data loss. | Create an automatic ticket for each failed backup with an escalation timer; report unresolved failures weekly. | Head of IT Operations | 2026-12-17 | Open | EV-004 | T-13 | None identified in the evidence provided. | Agreed | Agreed. | Failed-job tickets with escalation timers in operation; a re-test of the next quarter shows every failure retried or escalated within 24 hours. | Not yet due
F-12 | P1 | Restoration tests were not evidenced or not successful, and the control has no minimum frequency | Medium | Design deficiency and operating failure (evidence) | NS-OPS-02 (design) against the backup standard, which requires quarterly restoration testing. | Of 5 recorded restoration tests, 1 had no evidence and 1 ended Partial. The control states testing occurs 'as scheduling permits', which has no minimum frequency and is weaker than the quarterly requirement of the backup standard. | The control was written before the backup standard was updated. | Backups could be unrecoverable and the first discovery would be during a real incident. | Align the control with a quarterly minimum; require evidence retention; investigate and re-run the Partial test. | Head of IT Operations | 2026-12-17 | Open | EV-005;EV-022;EV-023;EV-024;EV-025 | T-15;T-14 | None identified. | Agreed | Agreed. The control text will be aligned to the quarterly requirement. | Control text aligned to quarterly testing; evidence retained for every test; the Partial restoration test re-run with a Pass result. | Not yet due
F-13 | P1 | No restoration test recorded for the Core Ledger or Data Warehouse (inconclusive pending confirmation) | High | Evidence insufficiency (not a confirmed control failure) | NS-OPS-02 and the backup standard: quarterly restoration testing of critical systems. | No restoration test is recorded for SYS-03 Core Ledger in 2026-Q1 or 2026-Q2, or for SYS-07 Data Warehouse in 2026-Q2. The restore register is maintained manually and its owner has not confirmed that it is complete (EV-005), so the absence of tests is not confirmed. Daily backups of the Core Ledger ran during the period. | Not determined: either tests were not run, or they were run and not recorded. | If tests were not run, the Core Ledger (Restricted data; low appetite for outages) could be unrecoverable. | Owner to confirm completeness of the register and provide evidence of any tests; if none were run, perform a ledger restoration test within 30 days. Internal Audit will reassess on receipt. | Head of IT Operations | 2026-11-17 | Inconclusive: awaiting management confirmation | EV-005 | T-14 | Daily backups ran for the Core Ledger during the period; backups alone do not demonstrate recoverability. | Agreed | The register owner is reviewing records; a ledger restoration test is scheduled for October regardless. | The register owner confirms completeness in writing, or a ledger restoration test is performed and evidenced. Internal Audit then updates the conclusion to confirmed or cleared. | Not yet due
F-14 | P1 | Weekly security alert reviews were missing, late, duplicated or lacked escalation | Medium | Operating failure and design deficiency | NS-LOG-02: weekly review within 5 business days of week end; high-severity alerts escalated (design: escalation is discretionary). | Of 25 weeks, 3 had no review, 2 were reviewed late, 2 had high-severity alerts with none escalated, and 1 record duplicated another. The control leaves escalation to analyst discretion. The recorded hash of the evidence file does not match its current hash (EV-006). | Review coverage depends on individual analysts; the SIEM does not enforce a weekly review task or a mandatory escalation decision. | High-severity alerts may not be actioned, and monitoring gaps can delay detection of incidents. | Make escalation of high alerts mandatory with a documented decision; schedule review tasks with tracking; control the review log so it cannot be edited after the fact. | IT Security Manager | 2026-12-17 | Open | EV-006 | T-16 | None identified. | Agreed | Agreed. | Control text requires an escalation decision for every high alert; four consecutive months of complete, timely reviews on a tamper-evident log. | Not yet due

## Management action plan
SIMULATED: fictional company, synthetic data, no real audit.
action_id | finding_id | finding_title | severity | action | owner_role | target_date | dependencies | status | completion_evidence | closure_criteria | retest_result
F-01/A1 | F-01 | Terminated employees retained active access to in-scope systems | High | Disable the 4 remaining active leaver accounts and open a security investigation of the post-termination login | IT Security Manager | 2026-09-25 |  | Completed (reported by management) | Management-supplied change log extract (simulated) | All leaver accounts disabled and re-tested on a fresh HR termination list; investigation report on the post-termination login approved by the Chief Risk Officer; evidence of the automated HR-to-IT reconciliation operating for one full month. | Fail: 1 of 4 records still non-compliant
F-01/A2 | F-01 | Terminated employees retained active access to in-scope systems | High | Automate deprovisioning from the HR termination feed and add a daily reconciliation of terminated employees to active accounts | IT Security Manager | 2026-11-17 | HR feed change release Q4 | In progress |  | All leaver accounts disabled and re-tested on a fresh HR termination list; investigation report on the post-termination login approved by the Chief Risk Officer; evidence of the automated HR-to-IT reconciliation operating for one full month.
F-02/A1 | F-02 | Administrator access granted without documented approval | High | Obtain retrospective system-owner approval or remove the access; require a ticket reference before an Admin role can be assigned; add Admin accounts to the monthly privileged access report. | Head of Platform Engineering | 2026-11-17 |  | Not started |  | Documented system-owner approval or removal for each Admin account without approval; ticket-reference enforcement shown in configuration evidence; Internal Audit re-performs the Admin population test.
F-03/A1 | F-03 | Quarterly user access reviews were late, incomplete, not independent or ineffective | High | Require reviewer independence in the control text; generate the review population from the system extract and reconcile it before attestation; escalate overdue reviews at day 30; include a leaver check in every review. | IT Security Manager | 2026-11-17 |  | Not started |  | Revised control text with an independence requirement; the next quarter's review evidenced as complete, on time, independent and reconciled to the system extract, with a leaver check.
F-04/A1 | F-04 | Service accounts without a valid owner | Medium | Assign owners; add owner recertification to the quarterly review; trigger reassignment from the leaver process. | Head of Platform Engineering | 2026-12-17 |  | Not started |  | Owners assigned to every service account; owner recertification added to the quarterly review; test of the service-account population shows zero accounts without a current owner.
F-05/A1 | F-05 | Multi-factor authentication not enabled on some human accounts, including an administrator | High | Enable MFA on the 3 accounts and disable local authentication for human users | IT Security Manager | 2026-09-25 |  | Completed (reported by management) | Management-supplied change log extract (simulated) | MFA flag verified enabled on the three accounts in the live console; local authentication for human users disabled (configuration evidence). | Pass: 3 of 3 records remediated
F-06/A1 | F-06 | Dormant and role-change access not removed | Medium | Disable the 4 dormant accounts | IT Security Manager | 2026-09-25 |  | Completed (reported by management) | Management-supplied change log extract (simulated) | Dormant accounts disabled and a re-run of the idle-account test shows no unexcepted accounts over 90 days; mover access removed and a mover review step evidenced for the next two transfers. | Pass: 4 of 4 records remediated
F-06/A2 | F-06 | Dormant and role-change access not removed | Medium | Remove retained mover access and add a mover review to the transfer workflow | IT Security Manager | 2026-12-17 | Workflow change in ITSM tool | In progress |  | Dormant accounts disabled and a re-run of the idle-account test shows no unexcepted accounts over 90 days; mover access removed and a mover review step evidenced for the next two transfers.
F-07/A1 | F-07 | Some access was granted before approval, or without an approval record | Low | Require a ticket reference at provisioning; report accounts without a ticket monthly. | Head of IT Operations | 2027-01-16 |  | Not started |  | Not applicable (risk accepted). Accepted by the risk owner; revisit if the exception rate exceeds tolerance at the next audit.
F-08/A1 | F-08 | Developers deployed their own changes to production | High | Technically enforce separation of developer and deployer roles in the pipeline; review pipeline permissions quarterly. | Head of Payments Engineering | 2026-11-17 |  | Not started |  | Pipeline configuration shows developer and deployer roles are separated; a re-run of the deployer-versus-developer test over the next quarter has zero exceptions.
F-09/A1 | F-09 | Normal changes lacked test evidence, independent approval or prior approval | Medium | Make test result, evidence reference and independent approver mandatory fields; block implementation without prior approval. | Change Manager | 2026-12-17 |  | Not started |  | Mandatory test, evidence and independent approver fields live in the change tool; a re-test over the next quarter's Normal changes has zero exceptions.
F-10/A1 | F-10 | Emergency changes approved retrospectively after the 2-business-day limit | Medium | Automate reminders at day 1 and escalation at day 2. | Change Manager | 2026-12-17 |  | Not started |  | Automated day-1 reminder and day-2 escalation in operation; next quarter's Emergency changes all approved within 2 business days.
F-11/A1 | F-11 | Failed backups of the Payments API were not re-run | Medium | Create an automatic ticket for each failed backup with an escalation timer; report unresolved failures weekly. | Head of IT Operations | 2026-12-17 |  | Not started |  | Failed-job tickets with escalation timers in operation; a re-test of the next quarter shows every failure retried or escalated within 24 hours.
F-12/A1 | F-12 | Restoration tests were not evidenced or not successful, and the control has no minimum frequency | Medium | Align the control with a quarterly minimum; require evidence retention; investigate and re-run the Partial test. | Head of IT Operations | 2026-12-17 |  | Not started |  | Control text aligned to quarterly testing; evidence retained for every test; the Partial restoration test re-run with a Pass result.
F-13/A1 | F-13 | No restoration test recorded for the Core Ledger or Data Warehouse (inconclusive pending confirmation) | High | Owner to confirm completeness of the register and provide evidence of any tests; if none were run, perform a ledger restoration test within 30 days. Internal Audit will reassess on receipt. | Head of IT Operations | 2026-11-17 |  | Not started |  | The register owner confirms completeness in writing, or a ledger restoration test is performed and evidenced. Internal Audit then updates the conclusion to confirmed or cleared.
F-14/A1 | F-14 | Weekly security alert reviews were missing, late, duplicated or lacked escalation | Medium | Make escalation of high alerts mandatory with a documented decision; schedule review tasks with tracking; control the review log so it cannot be edited after the fact. | IT Security Manager | 2026-12-17 |  | Not started |  | Control text requires an escalation decision for every high alert; four consecutive months of complete, timely reviews on a tamper-evident log.

## Exceptions
SIMULATED: fictional company, synthetic data, no real audit.
test_id | control_id | rule_id | record_id | detail
T-01 | NS-IAM-01 | R-IAM-06 | A-0209 | SYS-03 access granted 2026-05-19 before approval 2026-05-20
T-01 | NS-IAM-01 | R-IAM-06 | A-0358 | SYS-04 access granted 2026-04-14 before approval 2026-04-16
T-01 | NS-IAM-01 | R-IAM-06 | A-0359 | SYS-04 access granted 2026-05-04 before approval 2026-05-05
T-01 | NS-IAM-01 | R-IAM-07 | A-0352 | SYS-04 Standard access has no approval ticket/approver/date
T-01 | NS-IAM-01 | R-IAM-07 | A-0360 | SYS-04 Standard access has no approval ticket/approver/date
T-02 | NS-IAM-02 | R-IAM-01 | A-0132 | SYS-02 Payments Console Admin account still Active; employee E0360 terminated 2026-04-24; last login 2026-04-30 is 6 days AFTER termination
T-02 | NS-IAM-02 | R-IAM-01 | A-0171 | SYS-03 Ledger Accountant account still Active; employee E0199 terminated 2026-05-29
T-02 | NS-IAM-02 | R-IAM-01 | A-0218 | SYS-04 Reviewer account still Active; employee E0022 terminated 2026-03-20
T-02 | NS-IAM-02 | R-IAM-01 | A-0329 | SYS-04 Developer account still Active; employee E0354 terminated 2026-02-13
T-02 | NS-IAM-02 | R-IAM-02 | A-0038 | SYS-01 account disabled 2026-02-10, 7 business days after termination 2026-01-30 (limit 2)
T-02 | NS-IAM-02 | R-IAM-02 | A-0106 | SYS-02 account disabled 2026-03-23, 11 business days after termination 2026-03-06 (limit 2)
T-02 | NS-IAM-02 | R-IAM-02 | A-0286 | SYS-04 account disabled 2026-05-01, 15 business days after termination 2026-04-10 (limit 2)
T-02 | NS-IAM-02 | R-IAM-02 | A-0397 | SYS-05 account disabled 2026-05-01, 15 business days after termination 2026-04-10 (limit 2)
T-03 | NS-IAM-03 | R-IAM-08 | A-0039 | SYS-01 access retained after move Customer Support to Finance on 2026-03-23; no exception reference
T-03 | NS-IAM-03 | R-IAM-08 | A-0102 | SYS-02 access retained after move Operations to Risk and Compliance on 2026-04-17; no exception reference
T-04 | NS-IAM-04 | R-REV-01 | UAR-SYS-03-2026-Q1 | UAR-SYS-03-2026-Q1: due 2026-04-30, not completed by extract date 2026-07-15
T-04 | NS-IAM-04 | R-REV-02 | UAR-SYS-01-2026-Q2 | UAR-SYS-01-2026-Q2: reviewer E0357 holds Admin access on SYS-01 (reviewed own access)
T-04 | NS-IAM-04 | R-REV-03 | UAR-SYS-01-2026-Q1 | UAR-SYS-01-2026-Q1: completed 2026-07-10, 71 days after due 2026-04-30
T-04 | NS-IAM-04 | R-REV-04 | UAR-SYS-02-2026-Q2 | UAR-SYS-02-2026-Q2: attested 2026-07-07 but at least one terminated user's account remained Active (review did not detect it)
T-04 | NS-IAM-04 | R-REV-04 | UAR-SYS-03-2026-Q2 | UAR-SYS-03-2026-Q2: attested 2026-07-07 but at least one terminated user's account remained Active (review did not detect it)
T-04 | NS-IAM-04 | R-REV-04 | UAR-SYS-04-2026-Q1 | UAR-SYS-04-2026-Q1: attested 2026-04-08 but at least one terminated user's account remained Active (review did not detect it)
T-04 | NS-IAM-04 | R-REV-04 | UAR-SYS-04-2026-Q2 | UAR-SYS-04-2026-Q2: attested 2026-07-14 but at least one terminated user's account remained Active (review did not detect it)
T-04 | NS-IAM-04 | R-REV-05 | UAR-SYS-05-2026-Q1 | UAR-SYS-05-2026-Q1: reviewed 49 accounts; population at quarter end differs (incomplete review population)
T-05 | NS-IAM-05 | R-IAM-03 | A-0146 | SYS-02 service account A-0146: no owner recorded
T-05 | NS-IAM-05 | R-IAM-03 | A-0147 | SYS-02 service account A-0147: owner E0024 is terminated (2026-06-03)
T-05 | NS-IAM-05 | R-IAM-03 | A-0211 | SYS-03 service account A-0211: no owner recorded
T-05 | NS-IAM-05 | R-IAM-03 | A-0424 | SYS-05 service account A-0424: no owner recorded
T-06 | NS-IAM-06 | R-IAM-09 | A-0232 | SYS-04 account idle 194 days (limit 90); no exception reference
T-06 | NS-IAM-06 | R-IAM-09 | A-0309 | SYS-04 account idle 193 days (limit 90); no exception reference
T-06 | NS-IAM-06 | R-IAM-09 | A-0315 | SYS-04 account idle 161 days (limit 90); no exception reference
T-06 | NS-IAM-06 | R-IAM-09 | A-0398 | SYS-05 account idle 124 days (limit 90); no exception reference
T-07 | NS-IAM-07 | R-IAM-05 | A-0242 | SYS-04 Admin human account has MFA disabled
T-07 | NS-IAM-07 | R-IAM-05 | A-0390 | SYS-05 Standard human account has MFA disabled
T-07 | NS-IAM-07 | R-IAM-05 | A-0399 | SYS-05 Standard human account has MFA disabled
T-08 | NS-PAM-01 | R-IAM-04 | A-0170 | SYS-03 Admin account without documented ticket, approver, approval date
T-08 | NS-PAM-01 | R-IAM-04 | A-0388 | SYS-05 Admin account without documented ticket, approver, approval date
T-09 | NS-CHG-01 | R-CHG-02 | CHG-0049 | SYS-02 Normal change approved by its requester E0379
T-09 | NS-CHG-01 | R-CHG-02 | CHG-0112 | SYS-05 Normal change approved by its requester E0262
T-09 | NS-CHG-01 | R-CHG-03 | CHG-0004 | SYS-01 approval 2026-01-28T10:15:00Z after implementation 2026-01-27T09:00:00Z
T-09 | NS-CHG-01 | R-CHG-03 | CHG-0094 | SYS-04 approval 2026-06-23T10:15:00Z after implementation 2026-06-22T11:00:00Z
T-09 | NS-CHG-01 | R-CHG-03 | CHG-0115 | SYS-05 approval 2026-01-21T10:15:00Z after implementation 2026-01-20T12:15:00Z
T-10 | NS-CHG-02 | R-CHG-01 | CHG-0001 | SYS-01 Normal change: test result 'Not recorded', evidence ref 'none'
T-10 | NS-CHG-02 | R-CHG-01 | CHG-0002 | SYS-01 Normal change: test result 'Not recorded', evidence ref 'none'
T-10 | NS-CHG-02 | R-CHG-01 | CHG-0043 | SYS-02 Normal change: test result 'Not recorded', evidence ref 'none'
T-10 | NS-CHG-02 | R-CHG-01 | CHG-0046 | SYS-02 Normal change: test result 'Not recorded', evidence ref 'none'
T-10 | NS-CHG-02 | R-CHG-01 | CHG-0073 | SYS-03 Normal change: test result 'Not recorded', evidence ref 'none'
T-11 | NS-CHG-03 | R-CHG-04 | CHG-0012 | SYS-01 Emergency change deployed by its developer E0077
T-11 | NS-CHG-03 | R-CHG-04 | CHG-0050 | SYS-02 Normal change deployed by its developer E0211
T-11 | NS-CHG-03 | R-CHG-04 | CHG-0074 | SYS-03 Normal change deployed by its developer E0300
T-11 | NS-CHG-03 | R-CHG-04 | CHG-0116 | SYS-05 Normal change deployed by its developer E0272
T-12 | NS-CHG-04 | R-CHG-05 | CHG-0017 | SYS-01 Emergency change: retrospective approval 6 business days after implementation (limit 2)
T-12 | NS-CHG-04 | R-CHG-05 | CHG-0032 | SYS-01 Emergency change: retrospective approval 9 business days after implementation (limit 2)
T-12 | NS-CHG-04 | R-CHG-05 | CHG-0039 | SYS-01 Emergency change: retrospective approval 15 business days after implementation (limit 2)
T-13 | NS-OPS-01 | R-BKP-01 | BK-SYS-02-20260203 | SYS-02 backup failed 2026-02-03; no successful re-run recorded
T-13 | NS-OPS-01 | R-BKP-01 | BK-SYS-02-20260317 | SYS-02 backup failed 2026-03-17; no successful re-run recorded
T-13 | NS-OPS-01 | R-BKP-01 | BK-SYS-02-20260511 | SYS-02 backup failed 2026-05-11; no successful re-run recorded
T-13 | NS-OPS-01 | R-BKP-01 | BK-SYS-02-20260512 | SYS-02 backup failed 2026-05-12; no successful re-run recorded
T-13 | NS-OPS-01 | R-BKP-01 | BK-SYS-02-20260513 | SYS-02 backup failed 2026-05-13; no successful re-run recorded
T-14 | NS-OPS-02 | R-BKP-02 | SYS-03¦2026-Q1 | No restoration test recorded for SYS-03 in 2026-Q1 (completeness of restore register not confirmed, see EV-005)
T-14 | NS-OPS-02 | R-BKP-02 | SYS-03¦2026-Q2 | No restoration test recorded for SYS-03 in 2026-Q2 (completeness of restore register not confirmed, see EV-005)
T-14 | NS-OPS-02 | R-BKP-02 | SYS-07¦2026-Q2 | No restoration test recorded for SYS-07 in 2026-Q2 (completeness of restore register not confirmed, see EV-005)
T-15 | NS-OPS-02 | R-BKP-03 | RT-002 | SYS-01 restoration test 2026-05-19 has no supporting evidence
T-15 | NS-OPS-02 | R-BKP-04 | RT-004 | SYS-02 restoration test 2026-06-09 result 'Partial'
T-16 | NS-LOG-02 | R-LOG-01 | 2026-03-02 | No alert review recorded for week starting 2026-03-02
T-16 | NS-LOG-02 | R-LOG-01 | 2026-04-13 | No alert review recorded for week starting 2026-04-13
T-16 | NS-LOG-02 | R-LOG-01 | 2026-04-20 | No alert review recorded for week starting 2026-04-20
T-16 | NS-LOG-02 | R-LOG-02 | LR-006 | Week 2026-02-09 reviewed 2026-03-04, 13 business days after week end (limit 5)
T-16 | NS-LOG-02 | R-LOG-02 | LR-021 | Week 2026-05-25 reviewed 2026-06-22, 16 business days after week end (limit 5)
T-16 | NS-LOG-02 | R-LOG-03 | LR-012 | Week 2026-03-23: 3 high-severity alerts, 0 escalated
T-16 | NS-LOG-02 | R-LOG-03 | LR-023 | Week 2026-06-08: 2 high-severity alerts, 0 escalated
T-16 | NS-LOG-02 | R-LOG-04 | LR-004D | Week 2026-01-26: record duplicates another review (same reviewer, counts and completion time)

## Retest evidence
SIMULATED: fictional company, synthetic data, no real audit.
action_id | record_id | observed_on | observed_state | result
F-01/A1 | A-0132 | 2026-09-28 | Disabled | Pass
F-01/A1 | A-0171 | 2026-09-28 | Disabled | Pass
F-01/A1 | A-0218 | 2026-09-28 | Disabled | Pass
F-01/A1 | A-0329 | 2026-09-28 | Active | Fail
F-05/A1 | A-0242 | 2026-09-28 | MFA enabled | Pass
F-05/A1 | A-0390 | 2026-09-28 | MFA enabled | Pass
F-05/A1 | A-0399 | 2026-09-28 | MFA enabled | Pass
F-06/A1 | A-0232 | 2026-09-28 | Disabled | Pass
F-06/A1 | A-0309 | 2026-09-28 | Disabled | Pass
F-06/A1 | A-0315 | 2026-09-28 | Disabled | Pass
F-06/A1 | A-0398 | 2026-09-28 | Disabled | Pass